## Draft
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1
2
3
4
5
6
7
8
9
10
11
12
13
14
16
17
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## Index
S. no | Name of Checklist | Remarks
1 | Above and below ceiling check | C&I
2 | Water proofing | C&I
3 | Initial Water ponding | C&I
4 | Post Water ponding | C&I
5 | Pipe Inward | C&I
6 | Pipe Drainage | C&I
7 | Partition Marking | C&I
8 | Aluminium Cladding Work | C&I
9 | Partition 2nd side gyp | C&I
10 | Full glazed partition | C&I
11 | Partition above false ceiling | C&I
12 | Top and bottom sealant filling | C&I
13 | 1st side ply fixing | C&I
14 | 2nd side ply fixing | C&I
15 | Laminate fixing on the partition | C&I
16 | Laminate panelling (MDF or Ply) on the partition | C&I
17 | White board fixing on the partition | C&I
18 | 1st Coat paint clean on the texture | C&I
19 | Regular painting works | C&I
20 | POP bullmarking on the column | C&I
21 | POP Plastering | C&I
22 | Grid Ceiling Frame Work | C&I
23 | Tile fixing on the grid frame work | C&I
24 | Tile Laying | C&I
25 | Door's | C&I
26 | Vinyl Laying | C&I
27 | Self leveling | C&I
28 | Skirting / profiles | C&I
29 | Acoustic panel | C&I
30 | Glass door / partitions with Frosted film | C&I
31 | Factory storages | C&I
32 | Pelmat wing A | C&I
33 | Wallpaper / graphics installation | C&I
34 | Block work marking | C&I
35 | Block work (all size) | C&I
36 | Plastering | C&I
37 | Cinder & Screeding Work | C&I
38 | Sanitary fixtures installation | C&I
39 | Blinds installation | C&I
40 | Raised flooring | C&I
41 | Granite cladding and flooring | C&I
42 | Railing Works (SS & MS) | C&I
43 | FAPA - Sprinkler Works: Piping | MEP
44 | FAPA - Cabeling / Wiring | MEP
45 | FAPA - FIRE AND SMOKE DAMPERS | MEP
46 | UPS Installation | MEP
47 | HVAC - copper pipe laying | MEP
48 | HVAC -AHU | MEP
49 | HVAC -Cassette units | MEP
50 | HVAC -DiffuserGrill | MEP
51 | HVAC -Fan | MEP
52 | HVAC -Pipe Insulation | MEP
53 | HVAC -Piping | MEP
54 | HVAC - VAV INSTALLATION | MEP
55 | HVAC - DUCTING | MEP
56 | HVAC - DUCT INSULATION | MEP
57 | Electrical - Cable tray | MEP
58 | Electrical - conduiting | MEP
59 | Electrical - Earthing | MEP
60 | Electrical - Floor raceway | MEP
61 | Electrical - light fitting - Installing | MEP
62 | Electrical - LT Cabling | MEP
63 | Electrical - Panel-Instalation | MEP
64 | Electrical - Switch socket | MEP
65 | Electrical - Wiring works | MEP
66 | Electrical - Distribution board | MEP
67 | Electrical - CABLE LAYING | MEP
68 | Electrical - MCB & DB | MEP
69 | Structural Erection work | Structural
70
71

## Electrical - MCB & DB
Inspection Report No | SMPL/PJ/R07
Rev | 01 & 07-10-2024
Date/Time | 03-10-2025; 17:00
INSTALLATION CHECKLIST FOR MCB DB
Project: |  |  |  | Make:
Shop Drawing no: |  |  |  | DB no:
Description of DB:
S No: | Item Description | Yes | No | Not Applicable | Remarks
1 | Make and quality as per spec.
2 | DB frame grouted properly in wall (in floor if floor mounted). Frame is painted, aligned square with the DB and vertically in plumb.
3 | Unused knockouts of the DB are closed with rubber bushings
4 | DB is earthed properly at two points. Check that the paint at the earthing contact is removed.
5 | Internal earth connected to earthing bolt.
6 | All terminations in MCBs done with lugs.
7 | Circuit identification provided with ferrules on the wires.
8 | Incoming cable glanded properly. Gland is earthed. Gland is held firmly with check nut.
9 | DB name plate provided (Printed sticker / Aluminium plates glued and screwed)
10 | Doors of the DB opens fully and easily.
11 | Pad locking arrangement provided on the DB.
12 | All the wires have adequate loop, are dressed properly,
13 | DB cleaned thoroughly.
14 | All cables and wires meggered.
15 | Internal wiring (from Incomer to outgoing bus bars) done with factory formed cables.
Observations:
For contractor |  | For Consultant |  | For Client
Name: |  | Name: |  | Name:
Signature: |  | Signature: |  | Signature:
Date: |  | Date: |  | Date:

## CABLE LAYING
Inspection Report No | SMPL/PJ/R07
Rev | 01 & 07-10-2024
Date/Time
INSTALLATION CHECKLIST FOR CABLE LAYING
Project: |  | Make:
Shop Drawing no: |  | Location:
Cable From: |  | To:
Cable size: |  | Lid on tray / in ground:
S No | Item Description | Yes | No | Not Applicable | Remarks
Cable on the tray
1 | Make and quality as per spec.
2 | Cable tray / raceway laid as per approved drawing.
3 | Cable Jack and rollers used for drawing the cable. No twists formed during laying
4 | Cable dressed properly on the cable tray, clamps/ cable ties provided at every 900mm max.
5 | Cable identification tag is provided at both ends
6 | No bruises, damage to the cable.
7 | Adequate bending radius provided.(12d)
8 | Cable is supported throughout its length, cable is not hanging loose.
9 | Where cable passing through walls or floors ensure GI / PVC sleeve is provided.
Cable laid in ground
10 | Before laying the cable ensure trench depth is as per spec. (min 750mm for LT & 900mm for HT)
11 | All debris, filth and rocks removed from the trench.
12 | Sand bedding and brick lining is done as per details in the shop drawing / spec.
13 | Ensure Cables laid on sand bed side by side, no crossing of cables.
14 | Backfilling done with soft soil, remove stones, filth debris from the soil.
15 | Cable markers provided at every 10mtrs and at every change of direction OR as indicated in a drawing.
16 | Megger the cable after laying is over.
Observations:
For contractor |  | For Consultant |  | For Client
Name: |  | Name: |  | Name:
Signature: |  | Signature: |  | Signature:
Date: |  | Date: |  | Date:

## Structural Erection work
Installation Check List
Name of the Contractor | [6 empty] | Date:
Description of work / BOQ no |  | Structural Erection work
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  |  | Yes | No | Not Applicable | Remarks
1 | Check for erection layout at site.
2 | Check sequence of erection as per layout drawing & requirement
3 | Check availibity of fabricated material at site as per sequence
4 | Check for basic diemenions of fabricated material before erection
5 | Check procedure of stacking fabricated material at site.
6 | Check availibity & specification of bolts /hardware as per shop drawing
7 | Check availibity of required capacity crane with test certificate
8 | Check availibity of required chery picker with test certificate
9 | Check availibity of required scaffolding /ladder certified by VW safety Dept.
10 | Check availibity of required lifting material like wire rope,chain block,chain pulley with test certificate
11 | Check for safety training & instruction regarding PPE's to workers before erection
12 | Check for foundations as per civil & structural drawing
13 | Check for temporary tie/supports to erected items before leaving erection site.
14 | Check for alignment of main structure
15 | Check for erection of sub structure
16 | Check for alignment of total structure
17 | Check for nut bolt tightening report.
18 | Check for final touch up paint
19 | Check for readiness of structure for sheeting
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## FIRE AND SMOKE DAMPERS
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | FIRE AND SMOKE DAMPERS
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | Material is of correct thickness and type ( powder coated/ painted),
2 | Fusible link and springs in place.
3 | All nut bolts at flanges are in place & tightened, appropriate gasket used between flanges.
4 | No visible damage
5 | Wall opening around the damper is sealed properly
6 | Damper properly supported
7 | For motorised dampers:
8 | Adequate spece around the actuator for maintenance
9 | Power supply provided.
10 | FAS loop connection completed
Testing and commissioning
S. no | Action |  | Observation |  | Remarks
1 | Ensure that the specifications, drawing and O&M manual are available on site.
2 | Remove the fuse link and check if the blades close tightly
3 | Motorised Dampers
4 | Switch on power supply to the damper actuator
5 | Simulate a fire signal to the damper acuator
6 | Switch off power supply to the damper actuator
7 | Fire damper shall be normally open.
8 | Fire damper shall be normally open.
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## FAPA WIRING
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | FAPA WIRING
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | All materials used are as per approval and specification
2 | All materials used/installed are defect/damage free.
3 | Routing and layout of the cable is as per approved shop drawings and easily traceable.
4 | No joints in the cable. Joints allowed only at the devices/panel.
5 | Cables are dropped from as per device locations shown in approved drawing and sufficient length is available for termination.
6 | Proper identification label to be provided at terminals
7 | Testing should be done for continuity,earth fault,shorts etc
8 | Color coding followed as per spec.
9 | Ensure cables are fixed strongly with proper clip/clamp at minimum spacings as per specification and standards
10 | Sharp bends not allowed.
11 | cables are installed in proper alignment without over lapping
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## Distribution board
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | Distribution board
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | Ensure the DB is of approved make before installation
2 | Check whether the DB installed as per the approved GA drawing
3 | Check whether the location of the DB installed is as per the approved drawing
4 | Check whether the DB is concealed or surface mounted as per the drawing/user requirement
5 | Check for the hight of the DB from the FFL is as per the approved drawing
6 | Check for the proper mounting arrangement is done for the surface mounted DBs
7 | Check the Provision made for Incoming and outgoing cables are proper.
8 | Check the Provision made for earthing are proper.
9 | Ensure the naming done for the DB is in line with the requirement.
10 | Check for the civil fineshes done properly for the concealed DBs
11 | Check for the incoming and out going cables entry with correct size DC Glands.
12 | Check for the earthing is done properly
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## Sprinkler Works, Piping
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | Sprinkler Works, Piping
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | All materials are as per approval and specification
2 | Approved drawing is followed
3 | Pipe routing and layout is as per approved shop drawings
4 | Pipes sizes are as per approved shop drawing
5 | All materials used are new and in good condition without any rust
6 | Visually check wheteher all joints are weled/connected properly.
7 | Check proper supports and minimum spacing
8 | Check the pipe is aligned perfectly
9 | Flexible pipes are connected properly and tightened
10 | Primer/painting provided as per specification and standards
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## HVAC -Piping
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | HVAC -Piping
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | Appearance (Clean/Rusted)
2 | Piping Material (MS/GI)
3 | Thickness/Class of the pipe (Light/Medium/Heavy)
4 | Type of pipe (ERW/Seamless)
5 | Check spacing of the pipe support
6 | Saddles provided for chilled water pipes
7 | Jointing/Welding of the pipes confirms to good Workman ship
8 | Air vents are provided
9 | Fixing of the valves as per drawing
10 | Gasket for valves
11 | Drain plugs/valves are provided
12 | Positioning of valves (Proper/Improper)
13 | Check availability of loop for initial flushing
14 | Flushing of the chilled water piping after Joints welded
16 | Pipe sleeve for wall/ceiling crossing
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## HVAC -Pipe Insulation
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | HVAC -Pipe Insulation
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | Check that pipe Routing is in accordance with approved drawing
2 | Check all weld beads/fillets are visually satisfactory
3 | Check spacing of supports are correct for pipe size and standard/ spec. reqts.
4 | Check size & positioning of suspenders & Anchors per pipe size and std/Specs.
5 | Check the spacing between joints of the pipe conforms to applicable Std/Specs.
6 | Check for Straightness, Leveling, Alingment & Verticality of the pipes.
7 | Check flange joints for proper sealing with rubber gasket and tightening of fasteners
8 | Check that pipe-sleeves at walls/floors are as per approved drawing, and are cut flush with
9 | Check direction of NRV and Globe Valves; and adequate access for all valve-handles.
10 | Check finish/final paint coat of AG piping & support is smooth, without wrinkles, sags, runs, scratches and damages.
11 | Check proper insulation material used
12 | Check thickness of the material used
13 | check surface of the pipes are cleaned
14 | Check applicaion of the insulation without leaving air gaps
16 | check alluminum cladding with 26 G
17 | Application of the bitumen
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## HVAC -Fan
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | HVAC -Fan
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | Type of fan
2 | Anti-vibration mounts
3 | Foundation (as per manufacture drawing)
4 | Mounting of fan over foundation
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## HVAC -DiffuserGrill
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | HVAC -DiffuserGrill
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | Quality (Acceptable/ Unacceptable)
2 | Painting (Proper/ Imprpoper)
3 | Louvers (Straight/ Bent)
4 | Alignment- Proper/Improper
5 | Fixing/ Fasteners ( Proper/ Improper)
6
7
8
9
10
11
12
13
14
16
17
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## HVAC -Cassette units
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | HVAC -Cassette units
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | Delivary of 2 TR Cassette units As per Drawg
2 | Installation of Cassette units 2 nos
3 | Refrigerent pipe conection for Cassette Indoor units
4 | Erection of Condenser units on terrace as per Drwg.
5 | Refrigerent pipe conection for Condenser units on terrace
6 | Pressure testing for Ref.pipe
7 | Insulation for Refrigerant pipe
8 | Power wire conection for indoor to outdoor unit
9 | Drain pipe conection for Cassette units
10 | Insulation for Drain pipe
11 | Power conection for Cassette(Elec.Panel to Cassette unit )
12 | Commissioning of Cassette unit
13 | Fixing of Thermostate
14 | Microprocessor panel which should be possible to hook up to automation
16 | Installation of Voltage Stablizer near outdoor unit
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## HVAC -AHU
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | HVAC -AHU
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
FAN & ACCS :
1 | Type of mounting -: Floor / Ceiling
2 | Model
3 | Level of AHU over foundation
4 | Fan impeller
5 | Fan casing
6 | Belt guard check
7 | Cooling coil
8 | Drain provision
9 | Check for foundation, if any
10 | Belt size
11 | Motor & Fan pulley alignment
12 | Flange connection near coil
13 | Inspection door / locks
14 | Provision for inserting pressure sensor probe : (Filter side)
15 | MOTOR DRIVE :
16 | Motor capacity
17 | Insulation protection class
18 | Check for power terminals
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## Wiring works
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | Wiring works
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | Make and quality as per spec.
2 | Wires size as per drawing
3 | Colour coding as per drawing
4 | Any damage to Insulation?
5 | Proper identification/ferrules in circuit wires
6 | Wires / cables protected properly in switch /power sockets and at DB end
7 | Wires are connected with switch & sockets with proper lugs
8 | Insulation resistance test carried out(test report attached)
9 | Electrical continuity test carried out( test report attached)
10 | Earth continuity test carried out (test report attached)
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## Switch socket
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | Switch socket
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | Switch /panel socket location co-ordinated with interior drawing
2 | Switch /power sockets height & location as per drawing
3 | Switch box/power box fixed properly
4 | Conduits terminated in box properly
5 | Wires in Switch /power sockets terminated properly
6 | Polarity test carried out(test report attached)
7 | Functional test carried out(test report attached)
8 | Voltage between neutral and ground test carried out(test report attached)
9 | Sticker provided
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## Panel-Instalation
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | Panel-Instalation
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | Availability of approved shop drawing
2 | Panel thoroughly checked & cleaned
3 | Panel feeders as per GA drawing
4 | Location as per approved shop drawing
5 | Panel aligned properly
6 | Panel grouted properly
7 | No. of holes in the Gland Plate as per drawing
8 | All bus bars of the panel tightened properly
9 | Checking of all relays and their settings
10 | Earthing connected/slip connected strip
11 | All opening sealed properly
12 | Rubber mats provided in front of panel
13 | Meggering of panel & cables as per range
14 | Feeder identification as required
15 | Test Reports status
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## LT Cabling
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | LT Cabling
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | Physical inspection of insulation
2 | Cables are laid as per sizes specified and approved makes
3 | Cable dressed properly
4 | Cable supported properly
5 | Cable clamped /cable tie used
6 | Glanding done properly
7 | Gland earthing provided
8 | Cable tag provided
9 | Megger value in acceptable range
R-Y CORE
R-B CORE
Y-B CORE
N-E CORE
R-E CORE
Y- E CORE
B- E CORE
10 | No bends exceeding the acceptable range
11 | Cable free from tension
12 | Cable dressed inside Panel
13 | Cable tray / raceway laid as per approved drawing.
14 | Cable Jack and rollers used for drawing the cable. No twists formed during laying
15 | Cable dressed properly on the cable tray, clamps/ cable ties provided at every 900mm max.
16 | Adequate bending radius provided.(12d)
17 | Cable is supported throughout its length, cable is not hanging loose.
18 | Where cable passing through walls or floors ensure GI / PVC sleeve is provided.
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## light fitting - Installing
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | light fitting - Installing
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | Type of fixtures as per approved sample
2 | Location as per co-ordination drawing
3 | Marking of opening size for concealed light fittings
4 | Flexible conduit with adopter provided
5 | Wires terminated properly
6 | Lighting Control as per approved drawing
7 | Light fittings are secured properly
8 | Light fittings are clean including inside diffuser
9 | Wattage of lamp and colour of lamp (day light / warm light)
10 | Check any damage to fixtures
11 | Check transformer rating and termination
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## conduiting
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | Conduiting
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | Conduit material & size as per specification & approved drawing
2 | Conduiting is done as per approved layout drawing.
3 | MS conduits coupled with threaded joints only. Conduit joints are threaded properly.
4 | Adhesive applied at all joints for PVC conduits.
5 | Conduit joints are cleaned and smooth
6 | Conduit joints are free from burrs.
7 | Conduits are saddled properly (Spacer-saddles provided at every 600mm)
8 | Conduits terminates in junction box properly
9 | Conduits terminates in switch/socket box with check nut properly
10 | End cap/PVC bushings provided and unused openings sealed properly. Unused knockouts of the JBs are closed with rubber bushings
11 | Concealed conduits protected against ingress of mortar.
12 | Proper line & level maintained.
13 | Check nuts provided at the termination of conduits in the junction boxes, switch boxes, DB etc.
14 | Conduit joints to Flexible conduits done with coupler
16 | Fabricated conduit accessories like, bends JBs couplers used-smooth bends / offsets provided.
17 | Continuity test carried out from one end to the other.
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## Floor raceway
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | Floor raceway
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | Raceway size & material as per approved drawing & sample
2 | Layout as per approved shop drawing
3 | Coordinates as per drawing
4 | Raceways and JB's are supported properly from ceiling
5 | Raceway covers provided, fixed with screws.
6 | Junction boxes and ends of raceways protected against ingress of mortar during screeding.
7 | Minimum 30mm depth available above the top of raceway cover from the finished screed surface.
8 | Junction boxes and ends of raceways protected against ingress of mortar during screeding.
9 | Junction boxes are covered with thermacol and tape.
10 | Pull wire laid in raceway(for long run only)
11 | Raceway terminated/connected with junction box properly
12 | All joints sealed as per requirements/specifications
13 | Is Raceway cleaned ?
14 | Pull wire laid in raceway(for long run only)
15 | Measurement sheet enclosed
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## Earthing
Installation Check List
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | Earthing works
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S.No. | Inspection details |  | I round | II round | Remarks
1 | Size and make as per specification / BOQ
2 | Access to earth electrode, test points and main earth bars
3 | Type of earth pit (copper / G.I.)
4 | Test links installed, connections made to equipments
5 | The panels are earthed on both sides using suitable strips
6 | Earthing for server room
7 | Value of Earth pit
8 | Earthing chamber and plate to be properly finished
9 | Earthing pit Identifivation is done
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## Cable tray
Installation Check List For Cable tray
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | Cable tray
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | Cable ladder /tray size & quality of material as per approved shop drawing
2 | Trays installed/ erected as per layout drawing
3 | Bottom-of-tray level as per services co-ordination drawing.
4 | Grinding done on sharp edges.-all edges are smooth
5 | Touch-up paint applied at welding spots.
6 | Proper supports to ladder/tray -supports at every 1200mm.
7 | All supports in level and plumb-appropriate size of Hitech rod, anchor fastener used
8 | All Tees and bends are properly fixed-factory fabricated bends, offsets and accessories used
9 | All fish plates are properly fixed/tightened
10 | All earthing continuity links are properly fixed/tightened
11 | Extra supports cut / removed if any
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## UPS Installation
Installation Check List For UPS
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | UPS INSTALLATION
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Level 1 | Level 2 | Remarks
1 | UPS is installed in level
2 | Batteries are connected properly
3 | Terminations are done properly
4 | Output voltages tested found as under
5 | R-Y
6 | Y-B
7 | B-R
8 | R-N
9 | Y-N
10 | B-N
11 | Leakage voltage to earth between E-N
12 | Incoming and outgoing connections made properly
13 | Display charts are proper
14 | Display functions are proper
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## DUCT INSULATION
Installation Check List For Duct Insulation
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | DUCT INSULATION
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Yes | No | Remarks
1 | Type of insulation is as per approved specs( Elastomeric foam / Fiber glass )
2 | Thickness of the material used
3 | Surface of the ducts are cleaned
4 | Application of the adhesive
5 | Fixing of the insulation without leaving air gaps
Observations:
Contractor |  | Service vendor | Client / Architect
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## DUCTING
Installation Check List For Ducting
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | Duct installation
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Yes | No | Remarks
1 | Ducting Material used (GI/ALUMINIUM)
2 | Gauge & longest side dimension Confirms to IS 655
3 | Quality of Aluminium GI Sheets (Bright/Soiled)
4 | Folding (Proper / Improper)
5 | Guide Vanes/shoe joints in collars
6 | Bracing around ducting
7 | Duct supports spacing interval
8 | Center distance of rivets/nut bolts of angle flanges not to exceed 150 mm
9 | Gasket Thickness
10 | Quality of Gasket (Acceptable/Not Acceptable)
11 | Fixing of Gasket
12 | Galvanizing of MS angle frames
13 | Access door for all dampers
14 | Layout and Bottom Lvl of the duct as per coordinated services drawing
15 | Provision of return air ducts with acoustic Insulation (Noise attenuator)
16 | Diffuser plenum hanging with four supports
17 | Flexible ducts fixing with round clamps
18 | Round butterfly dampers fixing
19 | Duct must not cross any beam and column capital.
20 | Check routing and slope of drain pipes.
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## VAV INSTALLATION
Installation Check List For VAV
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | VAV installation
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Yes | No | Remarks
1 | VAVs are installed as per the Drawing & VAV Schedule
2 | Duct Acoustic Insulation Immediate after the VAV as per the Drawings
3 | Are VAVs installed in Level & supported on Four Sides
4 | Is VCD installed before the VAV as per Drawing
5 | Check the Direction of - Air Flow
6 | VAV's Airflow Sensing Tube is Plugged
7 | Thermostat Location & Cabling as per drawing
8 | Thermostats are Calibrated
9 | DP Sensor Configuration to VFD
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## copper pipe laying
Installation Check List For Copper pipe
Name of the Contractor |  |  |  |  | Date:
Description of work / BOQ no |  | copper pipe laying
Drawing no
Name of the cabin/loaction
Inspection Report No |  | SMPL/PJ/R07
Rev |  | 01 & 07-10-2024
S NO | Description |  | Yes | No | Remarks
1 | Check that pipe Routing is in accordance with approved drawing
2 | Check the supports are properly aligned & level
3 | Check spacing of supports are correct for pipe size and standard/ spec. reqts.
4 | Check copper pipe size as per std/Specs.
5 | Check the spacing between joints of the pipe conforms to applicable Std/Specs.
6 | Check for Straightness, Leveling, Alingment & Verticality of the pipes.
7 | Check for the pipes are protected with cable trays & covers
8 | Check all brazed joints are visually satisfactory
9 | check surface of the pipes are cleaned
10 | Check proper insulation material used
11 | Check applicaion of the insulation without leaving air gaps
Observations:
For contractor |  | For Consultant | For Client
Name: |  | Name: | Name:
Signature: |  | Signature: | Signature:
Date: |  | Date: | Date:

## Railing Works (SS & MS)
Quality Check List
Package |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  | Date/Time
Description of Work |  | Railing Works (SS & MS) | Inspected by |  | Name
Dwg Ref.No |  |  |  |  | Signature
Floor |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  | Yes | No | Remarks
1 | Material grade, thickness, and finish as per approved drawings
2 | Fabrication quality – proper welding, grinding, and smooth finish
3 | Posts and rails aligned correctly (vertical/horizontal level check)
4 | Secure anchoring with correct bolts or chemical anchors
5 | Safety compliance – correct height, spacing, and edge protection
6 | Surface treatment – polished SS or coated/painted MS to avoid corrosion
7 | Accessories (brackets, caps, joints) installed firmly and neatly
8 | Cleanliness maintained; weld marks and sharp edges removed
9 | Load/stability checked before handover
10 | Final inspection completed and client approval documented
Observations if any :
Note : The clearance obtained from services works is attached for reference
SMPL |  |  |  | Client/Consultant
Signature : |  |  |  |  | Signature :
Name : |  |  |  |  | Name :
Date : |  |  |  |  | Date :

## Granite cladding and flooring
Quality Check List
Vendor |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  | Date/Time
Description of Work |  | Granite cladding and flooring | Inspected by |  | Name
Dwg Ref.No |  |  |  |  | Signature
Floor |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  | Yes | No | Remarks
1 | Approved granite samples
2 | Uniformity of color/shade in granite
3 | Thickness of granite slabs
4 | Evenness of surface
5 | Granite size as per drawing
6 | Surface preparation before fixing
7 | Adhesive/epoxy thickness and application
8 | Slopes (if applicable)
9 | Pattern alignment and joint matching
10 | Joints filling and finishing
11 | Hollow areas check
12 | Cracks, chips, or damage inspection
13 | Level alignment and squareness
14 | Cleanliness around fittings and edges
15 | Polishing quality
16 | Protection during curing by polythene sheet / other methods
Observations if any :
Note : The clearance obtained from services works is attached for reference
Contractor/Vendor |  |  |  | Client/Consultant
Signature : |  |  |  |  | Signature :
Name : |  |  |  |  | Name :
Date : |  |  |  |  | Date :

## Partition Marking
Quality Check List
Package |  |  | CIVIL AND INTERIOR | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  | 2025-26/LOA/WORK/SMPL-ADMIN/014 | Date/Time |  | 2025-09-20 | 15:00
Description of Work |  |  | Partition Marking | Inspected by |  | Name | Chinna babu
Dwg Ref.No |  |  | As per flooring layout |  |  | Signature | Chinna babu
Floor |  |  | 10 TH FLOOR | Rev |  | 01 & 07-10-2024
Location |  |  | 10th floor
S. No | Description |  |  | Yes | No | Remarks
1 | Drawing No. |  |  | YES |  | Latest GFC
2 | Latest revision of the drawing |  |  | YES
3 | Right angle of the partition |  |  | YES
4 | Inner dimensions of the cabin |  |  | YES
5 | The marking of partition thickness |  |  | YES
6 | Reference from the column |  |  | YES
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature : |  | Mr. Venkatesh
Name : |  | Mr. Chinna babu |  |  |  | Name : |  | Mr. Venkatesh
Date : |  | 2025-09-20 |  |  |  | Date : |  | 2025-09-20

## Partition 2nd side gyp
Quality Check List
Package |  | Civil and interiors | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  | Date/Time
Description of Work |  | Partition Second side gyp closing | Inspected by |  | Name
Dwg Ref.No |  |  |  |  | Signature
Floor |  |  | Rev |  | 01 & 07-10-2024
Location | [6 empty] | Partition Second side gyp closing
S. No | Description |  | Yes | No | Remarks
1 | Light fixtures conduit laying completed
2 | Speaker conduit laying completed
3 | Volume control conduit laying completed
4 | Thermostat conduit laying completed
5 | Glasswool/Rockwool fixing completed
6 | Glasswool//Rockwool thickness checked
7 | Glasswool//Rockwool make checked
8 | Provision given for cable tray / conduit above false ceiling
9 | Electrical box fixing completed
10 | Data / voice cable pulling completed
Observations if any :
SMPL |  |  |  | Client/Consultant
Signature : |  |  |  |  | Signature :
Name : |  |  |  |  | Name :
Date : |  |  |  |  | Date :

## Full glazed partition
Quality Check List
Package |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | Full Glazed Partition & Door | Inspected by |  | Name
Dwg Ref.No | [5 empty] | Signature
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks
1 | Approved Shop drawing
2 | Dimensions
3 | Wooden support on the top
4 | Wooden thickness
5 | Wooden approved make
6 | Partition thickness
7 | Glass thickness
8 | Glass weather toughened / ordinary
9 | Aluminium /sapwood section thickness
10 | Laminate / veneer fixing pattern
11 | Laminate / Veneer thickness
12 | Groove size / thickness
13 | Beading fixing
14 | Beading thickness
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature : |  | Mr. Venkatesh
Name : |  | Mr. Chinna babu |  |  |  | Name : |  | Mr. Venkatesh
Date : | [5 empty] | Date :

## Pelmat
Quality Check List
Package |  |  | CIVIL AND INTERIOR | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  | 2025-26/LOA/WORK/SMPL-ADMIN/014 | Date/Time |  | 18.09.2025 | 10:00
Description of Work |  |  | Pelmet | Inspected by |  | Name | Mr. Chinna babu
Dwg Ref.No |  |  | 1.11.9.0 |  |  | Signature | Mr. Chinna babu
Floor |  |  | 10 TH FLOOR | Rev |  | 01 & 07-10-2024
Location |  |  | WING A
S. No | Description |  |  | Yes | No | Remarks
1 | Pelmet size, material, and finish as per drawing |  |  | YES |  | As per drawing
2 | Level and alignment properly maintained |  |  | YES
3 | Proper fixing with concealed fasteners |  |  | YES
4 | Edges finished cleanly, no visible damage |  |  | YES
5 | Gap and clearance for curtain/blind movement checked |  |  | YES
Observations if any : Work completed with satisfactory
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature : |  | Mr. Venkatesh
Name : |  | Mr. Chinna babu |  |  |  | Name : |  | Mr. Venkatesh
Date : |  | 18.09.2025 |  |  |  | Date : |  | 2025-09-20
Done

## Tile laying (Floor and wall)
Quality Check List
Inspection Report No: SMPL/PJ/R07
Rev no & Date: 01 & 07-10-2024
Name of company:
Description of Work: Tile Laying (Floor and wall)
Dwg Ref.No:
Location:
Date & Time of inspection:
S. No | Description | Yes | No | Remarks
A | Pre-Work Checks
1 | Consultant approval for WMS
2 | MEP clearance received
3 | Material Inspection (Tiles/Adhesive/Grout)
4 | Substrate level, clean, dry
5 | Tile layout & reference lines marked
B | During Work
1 | Mixing as per approved ratio (1:1 OPC 53 + 305 chemical)
2 | Adhesive applied uniformly with proper trowel
3 | Tile alignment checked regularly
4 | Level & plumb maintained
5 | Joint spacing (2–3 mm) with spacers
6 | No hollow sound on tapping
C | Post-Work Checks
1 | Proper grouting completed
2 | No lippage beyond tolerance
3 | No cracks, chips, stains
4 | Surface cleaned
5 | Protection sheet placed
6 | Completion photos taken
Observations if any :
Signature from Contractor |  | Signature from Project Manager/Architect/Consultant
Signature |  | Signature
Name |  | Name
Date |  | Date

## Raised flooring
Quality Check List
Package |  |  | Civil and interiors | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  | 2025-26/PO/WORK/INDEGENE-10TH FLOOR/069 | Date/Time
Description of Work |  |  | Raised flooring | Inspected by |  | Name | Chinna babu
Dwg Ref.No |  |  | As per flooring layout |  |  | Signature | Chinna babu
Floor |  |  | 10th floor | Rev |  | 01 & 07-10-2024
Location |  |  | MTP
S. No | Description |  |  | Yes | No | Remarks
1 | Check the Method Statemet Submitted by the vendor
2 | Check the existing concrete has to be cleaned and finished with 400 micron self levellening epoxy coat
3 | Check the Markings as per the architectural drawings.
4 | Check the size and thickness of tile.
5 | Check the raised flooring shall be installed as per tharchitectural drawings.
6 | Check the raised flooring system inclusive of under structure designed load
7 | Check the thickness of plywood for vertical supports
8 | Check the cutouts in flooring tiles for services
9 | Check the Adhesives used for laying vinyl floor
10 | Check the finshes with anti static laminate / anti static vinyl tile.
11 | Check the Seamless joints
12 | Check the PVC Trims and soft welding
13 | Check the levels and surface after Raised flooring.
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## Blinds installation
Quality Check List
Package |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | Blinds installation | Inspected by |  | Name
Dwg Ref.No | [5 empty] | Signature
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks |  | Description
1 | Type, material, and color as per approved sample
2 | Proper alignment and level maintained
3 | Smooth opening and closing operation
4 | Secure fixing of brackets and supports
5 | No physical damage, wrinkles, or stains
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## Sanitary fixtures installation
Quality Check List
Package |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | Sanitary fixtures installation | Inspected by |  | Name
Dwg Ref.No | [5 empty] | Signature
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks |  | Description
1 | Fixtures as per approved make and model
2 | Alignment and level properly maintained
3 | Proper sealing and support at joints
4 | No damage, scratches or stains on fixtures
5 | Water flow, leakage and drainage tested
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## Wallpaper& graphics install
Quality Check List
Package |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | Wallpaper / graphics installation | Inspected by |  | Name
Dwg Ref.No | [5 empty] | Signature
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks
1 | Material/design as per approved sample
2 | Surface cleaned and primed before application
3 | Alignment and joint matching maintained
4 | No wrinkles, bubbles or edge lifting
5 | Neat finishing at corners and terminations
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## Factory storages
Quality Check List
Package |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | Factory storages | Inspected by |  | Name
Dwg Ref.No | [5 empty] | Signature
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks
1 | Material, size and type as per approved drawing
2 | Proper installation and anchoring to floor/wall
3 | Level and vertical alignment checked
4 | No sharp edges, dents or paint damage
5 | Load-bearing capacity labels/markings fixed
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## Acoustic panel
Quality Check List
Package |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | Acoustic panel | Inspected by |  | Name
Dwg Ref.No | [5 empty] | Signature
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location | [7 empty] | Partition Second side gyp closing
S. No | Description |  |  | Yes | No | Remarks
1 | Care to be taken, not to damage the side finishes while installing panels.
2 | Panels to be checked for damaged acoustic boards.
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## Above & below ceiling check
Work completion Checklist
Project name: |  | Indegene Limited
Package: |  | Civil and Interior
Date |  | 2025-10-01
Doc number: |  | SMPL/PJ/R07
Issue No, Date: |  | 01 & 07-10-2024
S.no | Work Description |  |  |  | Above ceiling Completion |  |  | After ceiling Completion |  |  | Remarks
Location: |  |  |  | Vendor | YES | NO | NA | YES | NO | NA
1 | Above Ceiling checklist before closer of ceiling
| A | Fire Fighting
Painting of sprinkler main lines header
Support of Sprinkler main lines header
Painting of sprinkler branch pipe
Support of Sprinkler branch pipe lines
Check for Adiquate supports
Installation of Sprinkler Upright
Remove safey clip of Sprinkler Upright
Installation of Sprinkler Flexible pendent
Remove safey clip of Sprinkler pendent
Installation of Smoke detectors
Above false ceiling of Smoke detectors protected cover removed
Installation of Speaker
Installation of response indicator
Installation of LED Signages
| B | HVAC
Installation of Ducting, insulation, proper supports
Installation of VAV units with proper supports.
Installation power spur fuse of VAV unit.
Installation of VAV cone piece with support
Installation of Flexible with supporting
Installation of Mixer box & Diffusers.
Installation of Mixer box with slot grills.
Installation of VAV cabling to VAV integrator with conduits
Installation of Thermostat
Installation of Z piece / cross
Battery room exhaust unit with controls
| C | Electrical
Installation of BMS, TMS, Lighting, CCTV, AV, IT trunking including conduits draping.
Covers installation of BMS, TMS, Lighting, CCTV, AV, IT trunking with suppots.
connecting of earthing wire for all truncking/conduits.
Cabling of BMS, TMS, Lighting, CCTV, AV, IT if any
Installation of support for Light fixture
Installation of Light fixture
installation of lighting sensor
Emergency light with support
Installation of conduits with power points of Roller blends
| D | BMS | VAV Units termination
Installation cabling of Co2 sensors
Installation of Co2 sensors
| E | Access control
Check Conduiting location and executed with proper supports
Check for Cabling and termination
Check for installation of the device
| F | AV units
Installation of 100X50MM AV Trunking with support
80mm Dia hole for display cable access
32 mm conduits from speakers with junction box
Installation of Camera conduits
40mm dia Hole for camera cable access.
Installation of power cables, conduits, sockets etc
Installation of conduits with back box of data port.
Ceiling speaker conduits with cabling.
Installation of Speakers
Cabling of speaker, Camera, AV etc
Data networking
2 | Closing of all service penetration around the partitions
Check for above Ceiling partitions are closed using PU foam no gap is visible
Check for below Ceiling partition are closed as the specification
3 | Below false flooring works before installation of carpet
Innstallation of IT, AV Raceways
Innstallation of AV cabling
Installation of Networking cabling
Installation of power cabling
Installation of raceways covers
Installation of power socket box
Tiles cutout for cabling
Cleaning below false flooring
Alignment of False flooring
Carpet laying
PREPARED BY : Mr. |  |  |  |  | APPROVED BY : Mr.

## Initial Water ponding
QUALITY CHECKLIST FOR SITE WORKS WATER PROOFING
Name of the Project: |  | Date :
Location:
Name of the Contractor:
Drawing Ref. No.:
Doc number: |  | SMPL/PJ/R07
Issue No, Date: |  | 01 & 07-10-2024
Sl. No. | Description | YES NO NA
1 | Floor Cleaning
2 | Penetration/soundness check
3 | No.of water proof coating, If yes mention the number also.
4 | Floor level check
5 | Wall and floor Coving
6 | Core cut packing with gunny bag
CORRECTIVE ACTION PROPOSED- Item wise. If 'No' is marked, please specify reasons and thereafter corrective action proposed. (Add additional sheets, if necessary)
Comments:
Contractor's Rep.:
ARCHITECTURAL
STRUCTURAL
INTERIOR
SERVICES & UTILITY

## Post Water ponding
QUALITY CHECKLIST FOR SITE WORKS WATER POND INSPECTION
Name of the Project: |  | Date:
Location:
Name of the Contractor:
Drawing Ref. No.:
Doc number: |  | SMPL/PJ/R07
Issue No, Date: |  | 01 & 07-10-2024
Sl. No. | Description | Range in'mm' | Level Obtained (From R.F.L to F.F.L) in 'mm'
1 | Observation #01 - After initial water filling | 0 | 0
2 | Observation #02 - 0hrs - 1 hrs | 0 | 0
3 | Observation #03 - 1hrs - 12 hrs | 0<2.5 | 2.5
4 | Observation #04 - 12hrs -24hrs | 1.5<2.5 | 2.5
5 | Observation #05 - 24hrs- 48hrs | 2.5<5 | 5
Comments:
Contractor's Rep.: Client's Rep.:
ARCHITECTURAL
STRUCTURAL
INTERIOR
SERVICES & UTILITY

## Pipe Inward
QUALITY CHECKLIST - PIPE INWARD INSPECTION
Name of the Project: Indegene 10th floor |  | Date: 22-10-2025
Location: |  | MTP
Name of the Contractor: |  | CHANDRABHANU PLUMBING WORK
Drawing Ref. No.: |  | GFC
Doc number: |  | SMPL/PJ/R07
Issue No, Date: |  | 01 & 07-10-2024
Sl. No. | Description | YES NO NA
1 | Pipe Material as per Specification and BOQ
2 | Pipe Make as per Approval
3 | Pipe Thickness as pe Approval
4 | Pipe Weight per length as per Approval
5 | Shop Drawings approved
6 | No waterproofing is damaged
7 | No structural member is cut/damaged
8 | Layout correct as per shop drawings
9 | Tap off points in the installation located accurately
10 | Access points in the stacks are accessible
11 | Installation clamped at adequate points
12 | Jointing with Teflon tape
13 | Adequate concrete supports provided to pipes laid flat
14 | Pipes painted as per schedule
15 | Chases in walls/ ceiling made good
16 | Manufacturer's Test certificate Attached
CORRECTIVE ACTION PROPOSED- Item wise. If 'No' is marked, please specify reasons and thereafter corrective action proposed. (Add additional sheets, if necessary)
Comments: Manufacturer's Test certificate will be shared along with handing over documents
Signature of Contractor |  | Signature of CLIENT
Mr. Chinna babu Date: 22-10-2025 |  | Mr. Venkatesh Date: 22-10-2025
ARCHITECTURAL
STRUCTURAL
INTERIOR
SERVICES & UTILITY
1. CHW
2. FPS
3. DRAINAGE
4. INTERNAL SUPPLY

## Pipe Drainage
QUALITY CHECKLIST - PIPE DRAINAGE INSPECTION
Name of the Project: Indegene 10th floor |  | Date: 22-10-2025
Location: |  | MTP
Name of the Contractor: |  | CHANDRABHANU PLUMBING WORK
Drawing Ref. No.: |  | GFC
Doc number: |  | SMPL/PJ/R07
Issue No, Date: |  | 01 & 07-10-2024
Sl. No. | Description | YES NO NA
1 | Pipe Material as per Specification and BOQ
2 | Pipe Make as per Approval
3 | Pipe Thickness as pe Approval
4 | Pipe Weight per length as per Approval
5 | Shop Drawings approved
6 | No waterproofing is damaged
7 | No structural member is cut/damaged
8 | Layout correct as per shop drawings
9 | Tap off points in the installation located accurately
10 | Access points in the stacks are accessible
11 | Installation clamped at adequate points
12 | Jointing with Teflon tape
13 | Adequate concrete supports provided to pipes laid flat
14 | Pipes painted as per schedule
15 | Chases in walls/ ceiling made good
16 | Manufacturer's Test certificate Attached
CORRECTIVE ACTION PROPOSED- Item wise. If 'No' is marked, please specify reasons and thereafter corrective action proposed. (Add additional sheets, if necessary)
Comments: Manufacturer's Test certificate will be shared along with handing over documents
Signature of Contractor |  | Signature of CLIENT
Mr. Chinna babu Date: 22-10-2025 |  | Mr. Venkatesh Date: 22-10-2025
1. CHW
2. FPS
3. DRAINAGE
4. INTERNAL SUPPLY
ARCHITECTURAL
STRUCTURAL
INTERIOR
SERVICES & UTILITY

## Partition above false ceilin
Quality Check List
Package |  |  | Civil and interiors | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  | 2025-26/LOA/WORK/SMPL-ADMIN/014 | Date/Time |  | 2025-10-16 | 16:00
Description of Work |  |  | Partition above false ceiling | Inspected by |  | Name | Mr. Chinna babu
Dwg Ref.No |  |  | Partition drawings |  |  | Signature | Mr. Chinna babu
Floor |  |  | 10th floor | Rev |  | 01 & 07-10-2024
Location |  |  | MTP
S. No | Description |  |  | Yes | No | Remarks
1 | Partition fixing on top and bottom |  |  | Yes
2 | Gyp / MDF packing both side |  |  | Yes
3 | Above false ceiling partition frame |  |  | Yes
4 | Above false ceiling partition both side gyp / MDF fixing |  |  | Yes |  | Gypsum
5 | Gap gyp closing around the conduit |  |  | Yes
6 | Gap closing around the cable tray |  |  | Yes
7 | Gap closing around the duct |  |  | Yes
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature : |  | Mr. Venkatesh
Name : |  | Mr. Chinna babu |  |  |  | Name : |  | Mr. Venkatesh
Date : |  | 2025-10-16 |  |  |  | Date : |  | 2025-10-16

## Sealant filling
Quality Check List
Package |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | Top and bottom sealant filling | Inspected by |  | Name
Dwg Ref.No | [5 empty] | Signature
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks
1 | Top and bottom spandrels fixing
2 | Gap between glazing and the slab
3 | Glazing channels fixing or not
4 | Sealant approved make
5 | Sealant color
6 | Sealant quality
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## 1st side ply fixing
Quality Check List
Package |  |  | Civil and interiors | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  | 2025-26/LOA/WORK/SMPL-ADMIN/014 | Date/Time |  | 2025-10-15 | 16:00
Description of Work |  |  | 1st side ply fixing | Inspected by |  | Name | Mr. Chinna babu
Dwg Ref.No |  |  | Partition layout |  |  | Signature | Mr. Chinna babu
Floor |  |  | 10th | Rev |  | 01 & 07-10-2024
Location |  |  | MTP
S. No | Description |  |  | Yes | No | Remarks
1 | Approved Shop Drawing |  |  | Yes
2 | Aluminium / wood partition |  |  | Yes |  | Aluminium
3 | Dimensions |  |  | Yes
4 | L clamp screwing |  |  | Yes |  | Pan head 13/8 & CSK
5 | Ply approved make |  |  | Yes
6 | Ply wood thickness |  |  | Yes
7 | Screw / nail size |  |  | Yes |  | 25 mm
8 | Ply joints screwing |  |  | Yes |  | every 1 feet
9 | Ply fixing with proper screws |  |  | Yes |  | CSK / Self tapping
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature : |  | Mr. Venkatesh
Name : |  | Mr. Chinna babu |  |  |  | Name : |  | Mr. Venkatesh
Date : |  | 2025-10-15 |  |  |  | Date : |  | 2025-10-15

## 2nd side ply fixing
Quality Check List
Package |  |  | Civil and interiors | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  | 2025-26/LOA/WORK/SMPL-ADMIN/014 | Date/Time |  | 2025-10-15 | 16:00
Description of Work |  |  | 2nd side ply fixing | Inspected by |  | Name | Mr. Chinna babu
Dwg Ref.No |  |  | Partition layout |  |  | Signature | Mr. Chinna babu
Floor |  |  | 10th | Rev |  | 01 & 07-10-2024
Location |  |  | MTP
S. No | Description |  |  | Yes | No | Remarks
1 | Ply wood thickness |  |  | Yes |  | 12 mm & 18 mm
2 | Plywood approved make |  |  | Yes |  | Archid
3 | Screw / nail size |  |  | Yes |  | 25mm CSK
4 | Plywood joints screwing |  |  | Yes
5 | Plywood fixing with proper screwing |  |  | Yes |  | every 1 feet
6 | Light fixtures conduit laying |  |  | Yes
7 | Speaker conduit laying |  |  |  | NO | Layed over ceiling
8 | Volume control conduit laying |  |  |  | NO | Layed over ceiling
9 | Thermostat conduit laying |  |  |  |  | NA
10 | Glass wool fixing |  |  | Yes
11 | Glass wool thickness |  |  | Yes |  | 48 mm
12 | Glass wool make |  |  | Yes |  | Rockwool
13 | Provision given for cable tray / conduit above false ceiling |  |  | Yes
14 | Electrical box fixing |  |  | Yes
15 | Data / voice cable pulling |  |  | Yes
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature : |  | Mr. Venkatesh
Name : |  | Mr. Chinna babu |  |  |  | Name : |  | Mr. Venkatesh
Date : |  | 2025-10-15 |  |  |  | Date : |  | 2025-10-15

## Laminate fixing on the parti
Quality Check List
Package |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | Laminate fixing on the partition | Inspected by |  | Name
Dwg Ref.No | [5 empty] | Signature
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks
1 | Ply / MDF partition in right angle
2 | Ply/ MDF partition nail / screw fixing properly
3 | Veneer approved make
4 | Code no
5 | Grains
6 | Approved shop drawing
7 | Grains matching
8 | Veneer polishing
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## Laminate paneling
Quality Check List
Package |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | Laminate panelling (MDF or Ply) on the partition | Inspected by |  | Name
Dwg Ref.No | [5 empty] | Signature
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks
1 | Make of the laminate
2 | Shade of the laminate
3 | Thickness of the laminate
4 | Quality of the frames used for the panelling
5 | Gap between the frame work for the panelling
6 | Hardware(screws etc.) used for the panelling
7 | Workmanship of the frame work
8 | Thickness of the MDF/ Ply used
9 | Quality of the MDF/ Ply used
10 | Fixing details of the MDF/ Ply used
11 | Adhesive used for fixing the laminate
12 | Workmanship of the laminate fixing
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## Whiteboard on partition
Quality Check List
Package |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | White board fixing on the partition | Inspected by |  | Name
Dwg Ref.No | [5 empty] | Signature
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks
1 | Quality of the white board
2 | Shade of the white board
3 | Frame work of the partition
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## 1st Coat paint clean
Quality Check List
Package |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | 1st Coat paint clean on the texture | Inspected by |  | Name
Dwg Ref.No | [5 empty] | Signature
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks
1 | Smooth finish in plastering
2 | Application of primer
3 | Sanding with sand paper to smoothen lumps or hard surfaces on walls
4 | POP
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## painting
Quality Check List
Package |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | Painting | Inspected by |  | Name
Dwg Ref.No | [5 empty] | Signature
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks
1 | Check for Availability of approved shade details and moke up's
2 | Check for cleaning of wall& ceiling surface.Is it free from Dead mortar,Dirt,Dust,algae,Grease etc
3 | Check for application of putty(mist Coat) to achieve level and uniform surfaces,if required.
4 | Check for suitability & safety of scoffolding
5 | Check for wetting of surface to be painted
6 | Check for mixing of paint with water-Is it as per maufacurer's specifications.
7 | Check for proper covering of floor surface and other finished surface to avoid paint stains.
8 | Check for consistancy of paint (Colour variation / Viscocity)
9 | Check for time interval between two coats
10 | Check for no. of coats of paint and thickness.
11 | Check for removal of scaffolds and cleaning.
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## POP bullmarking on the colum
Quality Check List
Package |  |  | Civil and interiors | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Inspected by |  | Name | Mr. Chinna babu
Description of Work |  |  | POP bullmarking on the column |  |  | Signature | Mr. Chinna babu
Date/Time |  |  | 26-09-2025, 17:00 | Rev |  | 01 & 07-10-2024
Floor |  |  | 10th floor
Location |  |  | MTP
S. No | Description |  |  | Yes | No | Remarks
1 | Check with plum from ceiling to flooring wall undulation |  |  | Yes
2 | Mark at mid height of the column from FL |  |  | Yes
3 | If undulation is more than 2cm, Instruct for plastering |  |  | Yes |  | less than 2 cm
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  | Signature : |  | Mr. Venkatesh
Name : |  | Mr. Chinna babu |  |  | Name : |  | Mr. Venkatesh
Date : |  | 2025-09-26 |  |  | Date : |  | 2025-09-26

## Grid Ceiling Frame Work (2
Quality Check List
Vendor |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | Grid Ceiling Frame Work | Inspected by |  | Name | Mr. Chinna babu
Dwg Ref.No | [5 empty] | Signature | Mr. Chinna babu
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks
1 | L angle properly fastened on the true ceiling with specified anchor fasteners
2 | All the Frame work materials used as per specs
3 | Slotted angle grill areas both sides intermediate support given
4 | Vertical ends are properly supported with intermediate and L angle
5 | Surface finished as per the required ceiling level
6 | The frame is in right angle with wall ( every 2m to be Checked)
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## Tile fixing on the grid
Quality Check List
Vendor |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | Tile fixing on the grid frame work | Inspected by |  | Name | Mr. Chinna babu
Dwg Ref.No | [5 empty] | Signature | Mr. Chinna babu
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks
1 | Tiles checked for damages, size, and color uniformity before installation
2 | Grid alignment and level verified before tile placement
3 | Tiles fixed flush with grid, without gaps or sagging
4 | Tile locking clips or edge supports used as required
5 | Cut tiles properly trimmed and placed at periphery with neat finish
6 | No visible cracks, chips or unevenness after fixing
7 | Final cleaning done and surface free from dust or stains
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## Glass door & partitions
Quality Check List
Vendor |  |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  |  | Date/Time
Description of Work |  |  | Glass door / partitions with Frosted film |  | Inspected by |  | Name | Mr. Chinna babu
BOQ Ref.No | [6 empty] | Signature | Mr. Chinna babu
Floor |  |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | NA | Remarks
1 | Glass type, size, and thickness as per drawing
2 | Proper alignment and level of glass panels
3 | Frosted film applied as per approved design
4 | Edges polished and hardware fixed properly
5 | Clean finish without scratches or bubbles
Observations if any :
SMPL | [5 empty] | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  |  | Date :

## Doors
Quality Check List
Vendor |  |  |  |  | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  |  | Date/Time
Description of Work |  |  | Doors |  | Inspected by |  | Name | Mr. Chinna babu
BOQ Ref.No | [6 empty] | Signature | Mr. Chinna babu
Floor |  |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | NA | Remarks
1 | Approved Shop drawings
2 | Section of door frame
3 | Size of door frame
4 | Fixing of holdfasts
5 | Direction of door opening
6 | Frame finishing and polishing
7 | Groove between door frame and partition
8 | Installation of Door with hardwares
9 | Checking the door's levels after installation
Observations if any :
SMPL | [5 empty] | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  |  | Date :

## Self leveling
Quality Check List
Vendor |  |  |  | Inspection Report No |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | Self leveling | Inspected by |  | Name | Mr. Chinna babu
Dwg Ref.No | [5 empty] | Signature | Mr. Chinna babu
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks
1 | Approved material/sample used
2 | Surface cleaned & free of dust/debris
3 | Primer application checked
4 | Substrate moisture within limits
5 | Level pegs or gauges fixed
6 | Material mixed as per manufacturer’s guidelines
7 | Uniform application thickness
8 | Smooth and leveled surface achieved
9 | Edges finished properly
10 | Curing time observed
11 | Cracks, undulations checked
12 | Cleaning of adjacent areas
13 | Clearance from MEP services
14 | Ready for next finish layer (Tile/Carpet/etc.)
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## Skirting
Quality Check List
Vendor |  |  |  | Inspection Report No |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | Skirting, Corner Guards & Related Profiles | Inspected by |  | Name | Mr. Chinna babu
Dwg Ref.No | [5 empty] | Signature | Mr. Chinna babu
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks
1 | Material and finish as per approved sample/drawing
2 | Fixing alignment, level and joints checked
3 | Surface free from damage or scratches
4 | Neat edge termination and proper joint treatment
5 | Area cleaned and protection provided post-fixing
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## Vinyl Laying
Quality Check List
Vendor |  |  |  | Inspection Report No |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time
Description of Work |  |  | Vinyl Laying | Inspected by |  | Name | Mr. Chinna babu
Dwg Ref.No | [5 empty] | Signature | Mr. Chinna babu
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks
1 | Approved samples
2 | Approved make of carpet
3 | Approved make of adhesives
4 | Uniformity of colour / shade in marble
5 | Eveness of floor
6 | Tile size as per drawing
7 | Surface preperation
8 | Flooring pattern
9 | Joints
10 | Cleanliness and finishing near floor junction box
11 | Protection by Polythene sheet
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature :
Name : |  | Mr. Chinna babu |  |  |  | Name :
Date : |  | 2025-09-20 |  |  |  | Date :

## Water proofing
Quality Check List
Vendor |  | Hari tech | Inspection Report No |  | SMPL/PJ/R07
P.O Number |  | 87
Description of Work |  | WATER PROOFING | Inspected by |  | Name | Mr. Chinna babu
Dwg Ref.No |  | GFC |  |  | Signature | Mr. Chinna babu
Floor |  | 10th | Rev |  | 01 & 07-10-2024
No. | Description |  | Yes | No | Remarks
1. | General Inspection
a. | Whether area is free of dust and laitance |  | Yes
2. | Toilet Waterproofing
a. | Whether all concealed water supply and drainage lines are laid, installed and tested prior to applying waterproofing treatment. |  | Yes
b. | Ensure that during final installation of sanitary fixtures, the waterproofing is not damaged. |  | Yes
c. | Whether repairing to waterproofing is carried out if damaged during installation of fixtures. |  | Yes
d. | Whether all joints of sanitary fixtures installed and their sealing are tested for any leakages prior to covering / embedding. |  | Yes
e. | Whether efficacy of water tightness and waterproofing is tested by artificial flooding. |  | Yes
3. | Terrace Waterproofing
a. | Obtain detailed specifications from the agency for waterproofing. |  |  | NO | NOT applicable in our project
b. | Whether the top of surface to receive waterproofing treatment is cleaned of all loose foreign materials, oil and grease. |  |  | NO | NOT applicable in our project
c. | Whether all pipes and sleeves are installed prior to waterproofing. |  |  | NO | NOT applicable in our project
d. | Whether the base course is laid to required slopes. |  |  | NO | NOT applicable in our project
e. | Whether all pipe outlets are installed in position while finishing the treatment. |  |  | NO | NOT applicable in our project
f. | Whether the final finished surface is provided as required. |  |  | NO | NOT applicable in our project
g. | Whether the area is cured properly for required period. |  |  | NO | NOT applicable in our project
h. | Whether the efficacy of the treatment is tested by artificial flooding. |  |  | NO | NOT applicable in our project
i. | Whether the defects are rectified. |  |  | NO | NOT applicable in our project
Signature of Contractor |  |  | Signature of CLIENT
Mr. Chinna babu Date: 22-10-2025 |  |  | Mr. Venkatesh Date: 22-10-2025

## Block work
Quality Check List
Date/Time |  | 2025-09-26
Description of Work |  | Block work
Dwg Ref No |  | Block work drawing
Inspection Report No |  | SMPL/PJ/R07
Revision no |  | 01 & 07-10-2024
No | Description |  |  | Yes | No | Remarks
1 | Blocks checked for dimensions, cracks, moisture content & compliance with IS 2185 standards |  |  | Yes |  | As per BOQ specifications
2 | Mortar mix ratio verified as per approved specifications (e.g., 1:4 or 1:6 cement:sand) |  |  | Yes
3 | Courses laid in proper level and alignment with uniform mortar thickness (10–12 mm) |  |  | Yes
4 | Vertical joints staggered and properly filled; no continuous vertical joints |  |  | Yes
5 | Curing carried out for minimum 7 days to ensure strength and bonding |  |  | Yes
6 | Openings, inserts, conduits and chases planned and executed without damaging the block integrity |  |  | Yes
Signature of Contractor |  |  | Signature of CLIENT
Mr. Chinna babu |  |  | Mr. Venkatesh

## Block work marking
Quality Check List
Package |  |  | Civil and interior | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Date/Time |  |  | 26-09-2025, 18:00
Description of Work |  |  | Block work Marking | Inspected by |  | Name | Mr. Chinna babu
Dwg Ref.No |  |  | Block work drawing |  |  | Signature | Mr. Chinna babu
Floor |  |  |  | Rev |  | 01 & 07-10-2024
Location
S. No | Description |  |  | Yes | No | Remarks
1 | Latest revision of the drawing |  |  | Yes |  | As per latest GFC
2 | Right angle of the partition is proper from the ref point |  |  | Yes
3 | Inner dimensions of the cabin is proper |  |  | Yes
4 | The marking of partition thickness as per GFC |  |  | Yes
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature : |  | Mr. Venkatesh
Name : |  | Mr. Chinna babu |  |  |  | Name : |  | Mr. Venkatesh
Date : |  | 2025-09-26 |  |  |  | Date : |  | 2025-09-26

## Plastering
Quality Check List
Package |  | Civil and interior | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  | Date/Time |  |  | 15-10-2025 @ 3:00PM
Description of Work |  | Plastering | Inspected by |  | Name | Mr. Chinna babu
Dwg Ref.No |  | As per partition marking layout |  |  | Signature | Mr. Chinna babu
Floor |  | 10th | Rev |  | 01 & 07-10-2024
Location |  | MTP
S. No | Description |  | Yes | No | Remarks
Steps Prior to plastering
1 | Check for completion of preceding activities like fixing of service conduits, water supply and sanitation lines. |  | Yes
2 | Raking of Masonry joints and hacking on RCC surfaces. |  | Yes
3 | Check for removal of efflorescent materials. |  | Yes
4 | Cleaning and washing of Masonry and RCC surfaces. |  | Yes
5 | Check for safety and suitability of scaffolding. |  | Yes
Steps During Plastering
6 | Bull marks to be provided as per the thickness specified at intervel of 1.5m for eveness of plastered surface. |  | Yes
7 | Check for proper mixing of Mortar. |  | Yes
8 | Check for Mortar Mix proportion |  | Yes
9 | Check for proper installation of Plaster Mesh. |  | Yes |  | On transition end
10 | Thickness and number of coats of plastering. |  | Yes |  | 12-15 mm as average
11 | Check for true level, right angle, plumb, straight edge, sharp corners. |  | Yes
Steps after Plastering
12 | Right angles and Plumb checks. |  | Yes
13 | Check for removal of all dead mortar and debris.. |  | Yes
14 | Curing arrangements |  | Yes
Observations if any :
SMPL |  |  | Client/Consultant
Signature | Mr. Chinna babu |  | Signature | Mr. Venkatesh
Name | Mr. Chinna babu |  | Name | Mr. Venkatesh
Date | 2025-10-15 |  | Date | 2025-10-15

## POP Plastering
Quality Check List
Package |  |  | Civil and interior | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Inspected by |  | Name | Mr. Chinna babu
Description of Work |  |  | POP plastering |  |  | Signature | Mr. Chinna babu
Dwg Ref.No |  |  | As per partition marking layout | Rev |  | 01 & 07-10-2024
Floor |  |  | 10th
Date/Time |  |  | 15-10-2025 @ 3:00PM
S. No | Description |  |  | Yes | No | Remarks
1 | Check for the wall where POP is mentioned as per the drawings |  |  | Yes |  | As per requirement/drawing
2 | Check for the dryness of the wall surface |  |  | Yes
3 | Check for the quality of the POP material used. |  |  | Yes
4 | Check for the thickness of the material applied on the wall surface |  |  | Yes |  | 12-15mm Avg thickness
5 | Check for bullmarks with respect to verticality, horizontal, right angle of the POP |  |  | Yes
6 | Check for POP finished surface |  |  | Yes
7 | Check for All jambs and corners with plumb bobs. |  |  | Yes
8 | Check for the make |  |  | Yes |  | Gyproc
9 | Check for the air gaps |  |  | Yes
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature : |  | Mr. Venkatesh
Name : |  | Mr. Chinna babu |  |  |  | Name : |  | Mr. Venkatesh
Date : |  | 2025-10-15 |  |  |  | Date : |  | 2025-10-15

## Screeding
Quality Check List
Package |  |  | Civil and interior | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  |  | Inspected by |  | Name | Mr. Chinna babu
Description of Work |  |  | Cinder & Screeding Work |  |  | Signature | Mr. Chinna babu
Dwg Ref.No |  |  | As per partition marking layout | Rev |  | 01 & 07-10-2024
Floor |  |  | 10th | Inspection Request No
Date/Time |  |  | 15-10-2025 @ 3:00PM
S. No | Description |  |  | Yes | No | Remarks
1 | Is the layout marking and floor levels verified? |  |  | Yes |  | As per GFC
2 | Is the sub base cleaned before taking up the laying of Cinder & Screed? |  |  | Yes
3 | Water proofing membrane Sheet has no damage |  |  | Yes
4 | Are the material grades as per the specifications? |  |  | Yes
5 | Are the plumbing pipeline/conduits are laid as per the requirement? |  |  | Yes
6 | Is the level of pipeline verified? |  |  | Yes
7 | Is the Cinder & Screed laying being done uniformly? |  |  | Yes |  | Screed considered for 75mm
8 | Is the mix of the Cinder & Screed as per the specifications? |  |  | Yes
9 | Has the levels of the finished floor been checked before the setting of the Cinder? |  |  | Yes |  | taken from entry
10 | Is the finished floor being cured adequately? |  |  | Yes
11 | Is the level of the junction boxes in line with the finished floor level? |  |  | Yes
12 | Is the position of output cables and wire entry in place? |  |  | Yes
13 | Has the levels of the finished floor been checked before the setting of the screed? |  |  | Yes
14 | Is the finished floor being cured adequately? |  |  | Yes
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature : |  | Mr. Venkatesh
Name : |  | Mr. Chinna babu |  |  |  | Name : |  | Mr. Venkatesh
Date : |  | 2025-10-15 |  |  |  | Date : |  | 2025-10-15

## Aluminium Cladding Work
Quality Check List
Date/Time |  |  | 24-09-2025/ 16:00 | Inspection Report No |  |  | SMPL/PJ/R07
P.O Number |  |  | 2025-26/LOA/WORK/SMPL-ADMIN/014 | Inspected by |  | Name | Mr. Chinna babu
Description of Work |  |  | Aluminium Cladding Work |  |  | Signature | Mr. Chinna babu
Dwg Ref.No |  |  | Partition marking layout | Rev |  | 01 & 07-10-2024
Floor |  |  | 10th floor
S. No | Description |  |  | Yes | No | Remarks
1 | Check for GFC drawing |  |  | Yes
2 | Check for suitability & safety of scaffolding |  |  | Yes
3 | Check for the column/partition in plumb and at right angles |  |  | Yes
4 | Are all the necessary service works complete |  |  | Yes
5 | Check for the levels being maintained while doing cladding |  |  | Yes
6 | Check for the joints between the gypsum / Aluminium or G.I Stud / Wood as per the specifications |  |  | Yes
7 | Check for the correct screwing as per specified |  |  | Yes
Observations if any :
SMPL |  |  |  |  | Client/Consultant
Signature : |  | Mr. Chinna babu |  |  |  | Signature : |  | Mr. Venkatesh
Name : |  | Mr. Chinna babu |  |  |  | Name : |  | Mr. Venkatesh
Date : |  | 2025-09-24 |  |  |  | Date : |  | 2025-09-25